## Daily Status Reporting
Daily Status Report
Legend
Date |  |  | Status on track
Resource Name |  |  | Slight deviation
Reporting Manager |  |  | Not on track. Need attention
Tasks Execution Completion Status
Tasks Planned | Tasks Executed(yes/No) | Tasks Execution Status | Execution Effort(Hrs) | Complete (%) | Comments
Analysing the documents and assuming the Database tables | yes | finished | 3 | 100
Creating basic structure of spring Applications | yes | finished | 3 | 100
Creation of entities with required fields | yes | finished | 4 | 100
Creation of basic login and all other required modules | yes | finished | 4 | 100
Uploading of documents Module | yes | finished | 7 | 100
Downloading of documents Module | yes | finished | 6 | 100
Setting the status | yes | finished | 3 | 100
Checking the status | yes | finished | 4 | 100
Junit test cases | yes | finished | 4 | 100
Microservics-Eureka | yes | finished | 4 | 100
Microservics-Actuators,Swagger and Spring cloud | yes | finished | 5 | 100