## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Work Product Cross Reference/Details sheet | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 |  |  | US_ID 01 | Register | User |  | Medium |  |  | user has to first signup in order to login. For signing up particular details are needed. They are user ID,Name,email,Phone number,password,etc.
2 | 2 |  |  | US_ID 02 | User Login | Customer |  | Medium |  |  | After signing up, the user can login using userId and password. After logging in the customer can perform user related operations.
3 | 3 |  |  | US_ID 03 | Admin Login | Admin |  | Medium |  |  | Admin can login using Id and password given by developer. After logging in the admin can perform crud opertions.
4 | 4 |  |  | US_ID 04 | Making an appointment | User |  | High |  |  | After logging in, user can select a diagnostic center, test and date to book an appointment.
5 | 5 |  |  | US_ID 05 | Viewing an appointment | Customer |  | Medium |  |  | User can able to view appointment list and also the appointment status.
6 | 6 |  |  | US_ID 06 | Adding diagnostic center | Admin |  | Medium |  |  | Admin can add a diagnostic center by entering center details.
7 | 7 |  |  | US_ID 07 | Removing diagnostic center | Admin |  | Medium |  |  | Admin will be able to delete a diagnostic center by clicking the delete button over there.
8 | 8 |  |  | US_ID 08 | Adding Test | Admin |  | Medium |  |  | Admin can be able to add test by entering the required test details.
9 | 9 |  |  | US_ID 09 | Removing Test | Admin |  | Medium |  |  | Admin will be able to delete a test by clicking the delete button over there.
10 | 10 |  |  | US _ID 10 | Approve Appointmnet | Admin |  | High |  |  | Admin can be able to approve the users appointent based on the slots available.
12 | 12
13 | 13
16 | 16
17 | 17
18 | 18
19 | 19
20 | 20
21 | 21
22 | 22
23 | 23
24 | 24
25 | 25
26 | 26
27 | 27
28 | 28
29 | 29
30 | 30
31 | 31
32 | 32
33 | 33
34 | 34
35 | 35
36 | 36
37 | 37
38 | 38
39 | 39
40 | 40
41 | 41
42 | 42
43 | 43
44 | 44
45 | 45
46 | 46
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.

## Sprint Backlog (Scrum)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | 1 |  |  | US_ID 01 | Signup/Register | Customer/ Admin |  | Medium |  |  | Customer/Admin has to first signup in order to login. For signing up particular details are needed. They are Admin ID,Customer ID,Name,email,Phone number,password,etc.
2 | 2 |  |  | US_ID 02 | Login | Customer/ Admin |  | Medium |  |  | After signing up, the user can login using the particular ID. These ID,s are different for customer and admin.After logging in the customer and admin can perform their particular crud operations.
3 | 3 |  |  | US_ID 03 | Admin welcome | Admin |  | Medium |  |  | When the admin gets logged in into this welcome page, it shows the operations which only an admin can do
4 | 4 |  |  | US_ID 04 | Entities creation | Customer/ Admin |  | Medium |  |  | When the data is entered, it is stored in this tables
5 | 5 |  |  | US_ID 05 | Admin Crud Operations | Admin |  | Medium |  |  | After the admin gets logged in crud operations ilke add,delete,update and get user can be performed
6 | 6 |  |  | US_ID 06 | Center Crud operations | Admin |  | Medium |  |  | After logging in, the admin performs crud operations of center like adding a center, deleting and updating a center etc..
7 | 7 |  |  | US_ID 07 | Test Crud operations | Customer/ Admin |  | High |  |  | When admin/customer wants a particular test,with the help of operation they can obtain that particular test.
8 | 8 |  |  | US _ID 08 | Make Appointment | Customer |  | Medium |  |  | When the customer gets logged in, they can make a booking, view their booking and also delete or update their booking
9 | 9 |  |  | US_ID 09 | View Appointment | Customer |  | High |  |  | When the customer gets logged in and wants to check the appointment status on a particular date
10 | 10 |  |  | US_ID 10 | Approve Appointment | Admin |  | High |  |  | After the admin gets logged in crud operations ilke add,delete,update and get user can be performed
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Sprint - 2